## Table of contents
Topic | Who? | Priority | Target Deadline | Status | Notes
Mural |  |  |  |  | Links from Remy that could be used to fill in
**please hyperlink the document under column A
00. Landing page: Welcome to CMS' OSPO
What's in the guide
How to use it
Functional statement | Aayat | Low hanging fruit | 4.12.24 | Complete | Push this to the repo
Link to TRA | Aayat | Low hanging fruit | 4.12.24 | Complete
Contribution guidelines
01. Inbound |  |  |  |  | Should we put tier 0? Yes, we should. Nat can work on descriptions for each tier
Checklist for inbound repo (overview, licenses, adding code, responsibilities, one verison rule reviewers) |  |  |  | Does not exist yet
Repo analysis and metrics
SW inventory management |  |  |  |  | Might not be public. SCSTF
Acceptable licenses | Aayat | Low hanging fruit |  | Pending approval | This exists in TRA a little. No great guidance. Link to OSI Approved License List. "According to the TRA(LINK TO SECTION) it is recommended that (COPY-PASTE) and you can find the OSI Approved Licese list here(LINK) TRA open source licensing (link to only that anchor)
02. Outbound |  |  |  |  | Should we include a tier 0? Nat can include decriptions for each tier
Maturity models | Natalia | Low hanging fruit | V1 done by 3.22.24 | Complete | PR is up on repo, waiting for approval on tier description table
Checklist for outbound repo | Natalia | Low hanging fruit | 3.22.24 (tiers 1, 3, and 4) | Work in progress | Tier 1, 3, 4 is fully completed. working on tier 2 this week
Repo templates and linters | Natalia | Low hanging fruit | 4.12.24 | Complete | Repo template is done and linter is being worked on in two weeks.
How to grow your open source project |  |  |  |  | Bigger fruit that we will break into a separate ticket, TODO group has a gudie specifically for this, add gov specific things
Repo analysis and metrics, includes measuring maintainer responsiveness and issue metrics |  |  |  |  | Taking metrics outbound and turning them into internal.
Year in review (impact) | Intern
Data and visualizations
Achiving repos |  |  |  | Does not exist yet
Automation of manual workflows aka repo scaffolder | Natalia | Low hanging fruit | 4.12.24 | Complete | Intertwined with repo templates and linters, waiting for comcast OSPO for linters
03. Growing
Intro developer training |  | Low hanging fruit |  |  | opensource.dev, opensource.guide, https://github.com/todogroup/ospo-career-path/tree/main/OSPO-101
Federal policy guidance
508 training |  | Low hanging fruit
PRA |  | Low hanging fruit |  |  | Chizo and Mathias PRA playbook
Plain language |  | Low hanging fruit |  |  | Digital.gov has a bullet list. Remy posted this in slack. https://www.plainlanguage.gov/resources/checklists/checklist/
What is a license? Open source casebook, AGPL policy |  | hardmode
Reading List | Aayat | Low hanging fruit | 4.12.24 | Work in progress | Evolving doc. Let's create an issue template for people to submit items to add to reading list, with acceptance criteria (e.g. must be open licensed, must not be behind a paywall, etc...)
Conferences, public speaking and events | Aayat | Low hanging fruit | 4.12.24 | Work in progress | this one will need to broken up into multiple sections: applying to speak at conferences, running events, what conferences you should go to. Link to speaker roll out approval forms. Need to have "go" links, need to figure out how to set that up. Use this for list of events: https://foss.events/. todo group: https://todogroup.org/community/events/
Applying to speak at conference | Aayat | Low hanging fruit
How to run events | Aayat | Low hanging fruit |  |  | how to run online events.. what are the procedures to do so. Virtual event guide. There are forms from HHS and CMS on how to run events like slack and sharepoint. what is the flow to run an event on-campus or off-campus
Conferences we recommended | Aayat | Low hanging fruit |  |  | Are you thinking all of these can ge go/links once we get them in github?
Contributing upstream |  |  |  | Does not exist yet
How to work at DSAC (if you need help with engineering)
Bug bounty
Commercial licenses
Improving visability and open source project (in platform agnotic way)
Early career talent pipeline | Aayat | Low hanging fruit | 3.22.24 | Pending approval
OSPO newsletter
Want to start an OSPO | Aayat | Low hanging fruit | 3.22.24 | Pending approval | Objective 3.2 from CISA, following their roadmap and contrib to their guidance. We want this to be a model of other fed agencies starting OSPO. Listing out all the EO's and memos that point to OSPO or OSS. Need Remy to review the EO's
OSPO mindmap | Aayat | Low hanging fruit | 3.22.24 | Pending approval | Point at this. Potentially embed this in github
Management tools
Community relations
Strategy (how do we go about reaching out to communities?)
Recruiting developers
Code of conduct
Marketing open source projects
Diversity and inclusion
Building leadership (under tier 4)
Employee engagement (internal) |  |  |  | Does not exist yet
Ambassadors |  |  |  | Does not exist yet
04. Resources
OSPO tools | Intern
Glossary (Git and GitHub specific) | Natalia |  | 4.12.24 | Work in progress | Nat will convert this to markdown, provided as a resource for teams new to GitHub
FAQ |  |  |  |  | https://open.gsa.gov/oss-implementation/ & https://dodcio.defense.gov/Open-Source-Software-FAQ/
History of open source at CMS (QPP open source pilot, look at TRA)