## Table of contents
Topic | Who? | Priority | Target Deadline | Status | Notes
Mural |  |  |  |  | Links from Remy that could be used to fill in
**please hyperlink the document under column A |  |  |  |  | Github OSPO guide
00. Landing page: OSPO (ReadMe)
What's in the guide (Table of Contents, list of directories) | Aayat |  |  | Committed to repo
How to use it
Functional statement | Aayat | Low hanging fruit | 4.12.24 | Committed to repo | Push this to the repo
Link to TRA | Aayat | Low hanging fruit | 4.12.24 | Committed to repo
Link to OSS policy
Contribution guidelines
0.5. Main Root
Acknowledgements
Policies (Open Source Policy, Responsible Disclosure Policy)
Public Domain Notice
SECURITY.md | Remy | Low hanging fruit |  | Committed to repo
CONTRIBUTING.md | Remy | Need consult with Remy | 06.08.24 | Work in progress
CODE_OF_CONDUCT.md | Remy | Low hanging fruit |  | Commit to repo
COMMUNITY_GUIDELINES.md | Remy | Low hanging fruit |  | Committed to repo
01. Inbound |  |  |  |  | Should we put tier 0? Yes, we should. Nat can work on descriptions for each tier
Checklist for inbound repo (overview, licenses, adding code, responsibilities, one verison rule reviewers) |  |  |  | Does not exist yet
Repo analysis and metrics
SW inventory management |  |  |  |  | Might not be public. SCSTF
Acceptable licenses | Aayat | Low hanging fruit |  | Committed to repo | This exists in TRA a little. No great guidance. Link to OSI Approved License List. "According to the TRA(LINK TO SECTION) it is recommended that (COPY-PASTE) and you can find the OSI Approved Licese list here(LINK) TRA open source licensing (link to only that anchor)
02. Outbound |  |  |  |  | Should we include a tier 0? Nat can include decriptions for each tier
Maturity models | Natalia | Low hanging fruit | V1 done by 3.22.24 | Committed to repo | PR is up on repo, waiting for approval on tier description table
Checklist for outbound repo | Natalia | Low hanging fruit | 3.22.24 (tiers 1-4) | Committed to repo | Tier 1-4 are complete
Repo templates and linters | Natalia | Low hanging fruit | 4.12.24 | Committed to repo | Repo template is done and linter is being worked on in two weeks.
How to grow your open source project | Aayat | Low hanging fruit |  | Work in progress | Bigger fruit that we will break into a separate ticket, TODO group has a gudie specifically for this, add gov specific things
Repo analytics and metrics
Measuring maintainer responsiveness |  |  |  |  | Add issue metrics
Year in review (impact) | Intern
Data and visualizations | Intern |  |  |  | Open data and content. Link to data.cms.gov . You should use creative commons. Link to CMS gource repo, pycon poster repo, and decks repo. Point to best practices instead of re-creating. Check out data viz on metrics repo
Achiving repos | Intern |  |  | Does not exist yet
Automation of manual workflows aka repo scaffolder | Natalia | Low hanging fruit | 4.12.24 | Complete | Intertwined with repo templates and linters, waiting for comcast OSPO for linters. Nat will commit to repo
Github Management Policy | Natalia |  |  | Work in progress
03. Growing
Intro developer training |  | Low hanging fruit |  |  | opensource.dev, opensource.guide, https://github.com/todogroup/ospo-career-path/tree/main/OSPO-101
Federal policy guidance
508 training | Aayat | Low hanging fruit |  | Committed to repo
PRA | Aayat | Low hanging fruit |  | Committed to repo | Chizo and Mathias PRA playbook
Plain language | Aayat | Low hanging fruit |  | Committed to repo | Digital.gov has a bullet list. Remy posted this in slack. https://www.plainlanguage.gov/resources/checklists/checklist/
AI Guidance |  |  |  |  | Link to AI explorers repo, link to HHS trustworthy AI playbook (https://www.hhs.gov/sites/default/files/hhs-trustworthy-ai-playbook.pdf ), AI.gov.
What is a license? Open source casebook, AGPL policy |  | hardmode
Reading List | Aayat | Low hanging fruit | 4.12.24 | Work in progress | Evolving doc. Let's create an issue template for people to submit items to add to reading list, with acceptance criteria (e.g. must be open licensed, must not be behind a paywall, etc...) Polish this up then commit to repo
Conferences, public speaking and events | Aayat | Low hanging fruit | 4.12.24 | Work in progress | this one will need to broken up into multiple sections: applying to speak at conferences, running events, what conferences you should go to. Link to speaker roll out approval forms. Need to have "go" links, need to figure out how to set that up. Use this for list of events: https://foss.events/. todo group: https://todogroup.org/community/events/
Applying to speak at conference | Aayat | Low hanging fruit |  | Work in progress | Asked in general about sharepoint link. It says I have to request access. Requested access on 5/8
How to run events | Aayat | Low hanging fruit |  |  | how to run online events.. what are the procedures to do so. Virtual event guide. There are forms from HHS and CMS on how to run events like slack and sharepoint. what is the flow to run an event on-campus or off-campus
Conferences we recommended | Aayat | Low hanging fruit |  | Work in progress | Are you thinking all of these can ge go/links once we get them in github? look at conference ticket on kanban board. Ask in the CMS OC channel who owns go links? go.cms.gov
Contributing upstream |  |  |  | Does not exist yet
How to work at DSAC (if you need help with engineering) | Aayat |  |  | Committed to repo | No go links at CMS. Blaine sent what he has created to onboard engineers: https://github.cms.gov/DSAC/dev-onboarding
Bug bounty
Commercial licenses
Improving visability and open source project (in platform agnotic way)
Early career talent pipeline | Aayat | Low hanging fruit | 3.22.24 | Committed to repo
OSPO newsletter | Intern
Want to start an OSPO | Aayat | Low hanging fruit | 3.22.24 | Committed to repo | Objective 3.2 from CISA, following their roadmap and contrib to their guidance. We want this to be a model of other fed agencies starting OSPO. Listing out all the EO's and memos that point to OSPO or OSS. Need Remy to review the EO's
OSPO mindmap | Aayat | Low hanging fruit | 3.22.24 | Committed to repo | Point at this. Potentially embed this in github
Management tools
Community relations
Strategy (how do we go about reaching out to communities?)
Recruiting developers
Guidance around code of conduct |  |  |  |  | Maturity model repo scaffoder code of conduct (lower case)
Marketing open source projects
Diversity and inclusion
Building leadership (under tier 4)
Employee engagement (internal) |  |  |  | Does not exist yet
Ambassadors |  |  |  | Does not exist yet
04. Resources
OSPO tools | Intern
Glossary (Git and GitHub specific) | Natalia |  | 4.12.24 | Committed to repo | Nat will convert this to markdown, provided as a resource for teams new to GitHub
FAQ |  |  |  |  | https://open.gsa.gov/oss-implementation/ & https://dodcio.defense.gov/Open-Source-Software-FAQ/
History of open source at CMS (QPP open source pilot, look at OSPO policy) | Aayat |  |  | Work in progress
Case studies
XZ case study
Innersource
Data write up from Pat on Databricks |  |  |  |  | https://cmsgov.slack.com/archives/CHDF1ELCQ/p1706721249261169?thread_ts=1706653649.523139&cid=CHDF1ELCQ
AI HHS ChatGPT |  |  |  |  | hhsgpt.hhs.gov & link to AI explorers
Want to work at DSAC (onboarding for devs) |  |  |  |  | Move the md from growing to innersource directory